## Sheet1
Project week	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22
Tasks	Planning					Development										Evaluation			Reserve

Report (chapters)
Planning report			x	x	x
Problem formulation			x	x	x
Introduction					x	x
Background					x	x	x
Global Illumination						x	x	x	x
Framework								x	x	x
Platform								x	x				x	x	x
Proposed Method									x	x	x	x	x	x	x
Results														x	x	x	x	x
Discussion																	x	x
Conclusion																	x	x
Abstract																	x	x
Acknowledgements																	x	x
Proof reading																		x	x	x
Corrections																			x	x
Report																		Draft	Rev.	Final
Reflection document																						x
Half-time check											x
Opposition														Find			Preparation				Perform
Presentation																	Preparation				Perform
Meeting	Weekly
Week	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27

																			Last updated		2016-02-25