## Sheet1
Project week	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29
Tasks	Planning					Development												Evaluation			Reserve	Reserve	Reserve	Reserve	Reserve	Reserve	Reserve
						Desktop implementation						Mobile implementation			Optimization			Summer break (not available for presentation)
Report (chapters)
Planning report			x	x	x
Problem formulation			x	x	x
Introduction					x	x
Background					x	x	x
Global Illumination						x	x	x
Framework							x	x				x	x
Platform												x	x	x	x	x	x
Voxel Cone Tracing								x	x	x	x	x	x	x	x
Results										x	x			x		x	x	x	x
Discussion																	x	x	x	x	x
Conclusion																	x	x	x	x	x
Abstract																		x	x
Acknowledgements																		x	x
Proof reading																		x	x	x
Corrections																				x	x	x
Report																			Draft		Rev.	Final
Reflection document																													x
Half-time check											x
Opposition																Find								Preparation				Perform
Presentation																								Preparation				Perform
Meeting	Weekly
Week	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34

																			Last updated:		2016-03-04